## Product Backlog
Final PoC Project | [6 empty] | Story point estimation
# | REQ ID | Features / Requirements - Level 1 | Features / Requirements - Level 2 | Release Phase/Milestone | Priority | Status | Initial Estimation | Sprint |  | Remarks
[7 empty] | 0 | 1 | 2
[7 empty] | 59 | 38 | 0
Application Management / Administration
1 | REQ1 | Database generation
|  |  | Class Diagram | Release-1 | P2 | Completed | 8 | 3
|  |  | Database Schema | Release-1 | P2 | Completed | 5 | 3
|  |  | Creative Models | Release-1 | P3 | Completed | 8 | 7
|  |  | Integrating with My SQL Server | Release-1 | P3 | Completed | 3 | 1
2 | REQ2 | New User Registration | Adding and implementing classes for Registartion | Release-1 | P1 | Completed | 3 | 4
|  |  | Adding Business layer for registartion | Release-1 |  | Completed | 3 | 1
|  |  | Creating Controller API | Release-1 |  | Completed | 3 | 2
|  |  | MVC for registration | Release-1 |  | Completed | 3 | 2
|  |  | UI design for registration | Release-1 |  | Completed | 6 | 5
|  |  | UI design for header | Release-1 |  | Completed | 6 | 4
|  |  | Test cases for Registration | Release-1 |  | Completed | 4 | 3
3 | REQ3 | Login and Logout | Adding and implementing classes for Login and Logout | Release-1 | P1 | Completed | 4 | 2
|  |  | Adding Business layer for Login and Logout | Release-1 |  | Completed | 3 | 1
|  |  | Creating Controller API | Release-1 |  | Completed | 3 | 2
|  |  | MVC for Login and Logout | Release-1 |  | Completed | 3 | 3
|  |  | Rediecting Logic | Release-1 |  | Completed | 2 | 2
|  |  | UI for Login and Logout | Release-1 |  | Completed | 6 | 4
|  |  | Test cases for Login and logout | Release-1 |  | Completed | 3 | 3
4 | REQ4 | Forgot Password | Adding Logic in API | Release-1 |  | Completed | 4 | 2
|  |  | Creating MVC | Release-1 |  | Completed | 3 | 3
|  |  | UI design for Forgot Password | Release-1 |  | Completed | 4 | 3
|  |  | Test cases for Forgot Password | Release-1 |  | Completed | 2 | 2
5 | REQ5 | User Dashboard | Adding and implementing classes | Release-1 |  | Completed | 4 | 2
|  |  | Adding Business layer for Booking seat | Release-1 |  | Completed | 3 | 2
|  |  | Creating Controller API | Release-1 |  | Completed | 3 | 2
|  |  | MVC for Booking seat | Release-1 |  | Completed | 5 | 4
|  |  | View Pass | Release-1 |  | Completed | 6 | 8
|  |  | Modify Booking | Release-1 |  | Completed | 3 | 3
|  |  | Cancel Booking | Release-1 |  | Completed | 3 | 3
|  |  | UI for view seat/meeting pass | Release-1 |  | Completed | 8 | 8
|  |  | UI for seat Booking | Release-1 |  | Completed | 8 | 7
|  |  | UI for Status card | Release-1 |  | Completed | 5 | 2
|  |  | UI for redirecting to notification, profile and logout | Release-1 |  | Completed | 6 | 4
6 | REQ6 | Test cases for Seat Booking | Adding Booking seat test cases | Release-1 |  | Completed | 1 | 2
|  |  | Modify Booking seat test cases | Release-1 |  | Completed | 1 | 2
|  |  | Cancel Booking seat test cases | Release-1 |  | Completed | 1 | 1
|  |  | Get all Booking seat test cases | Release-1 |  | Completed | 1 | 2
7 | REQ7 | User Profile | Adding Interface for employee | Release-1 |  | Completed | 2 | 3
|  |  | Implemnting classes for employee | Release-1 |  | Completed | 2 | 2
|  |  | Adding Business layer for employee | Release-1 |  | Completed | 1 | 2
|  |  | Creating API Controller | Release-1 |  | Completed | 3 | 2
|  |  | MVC for Employee Controller | Release-1 |  | Completed | 4 | 2
|  |  | Test cases for Add employee | Release-1 |  | Completed | 1 | 2
|  |  | Test cases for Modify employee | Release-1 |  | Completed | 1 | 3
|  |  | Test cases for Delete employee | Release-1 |  | Completed | 1 | 2
|  |  | Test cases for get all employee | Release-1 |  | Completed | 1 | 3
|  |  | UI design for profile | Release-1 |  | Completed | 5 | 3
8 | REQ8 | REQ08 - Continous Integration | CI/CD Pipeline and Azure app service | Release-1 |  | Completed | 6 | 7
|  |  | Boards in azure devops | Release-1 |  | Completed | 8 | 7
9 | REQ9 | Notification |  | Release-2
|  |  | Notification for Booked Seat | Release-2 |  | Not Started
|  |  | UI functionality for notification | Release-2 |  | Not Started
|  |  | Test case preparation and Unit Testing | Release-2 |  | Not Started
10 | REQ10 | Seat Booking and Tracking
|  |  | View Floor Map with availabel and booked seats | Release-2 |  | Not Started
|  |  | Select Floor and Book Seat | Release-2 |  | Not Started
|  |  | UI Functionality for seat booking and tracking | Release-2 |  | Not Started
|  |  | Test case preparation and Unit Testing | Release-2 |  | Not Started
11 | REQ11 | Admin functionalities
|  |  | Create booking | Release-2 |  | Not Started
|  |  | View and Record Booking Details | Release-2 |  | Not Started
|  |  | Approve and Reject Booking request | Release-2 |  | Not Started
|  |  | Scan QR and retrieve details | Release-2 |  | Not Started
|  |  | Add/Delete Seat | Release-2 |  | Not Started
|  |  | Add/Delete Room | Release-2 |  | Not Started
|  |  | Add/Delete Floor | Release-2 |  | Not Started
|  |  | UI Functionality for Admin functionalities | Release-2 |  | Not Started
|  |  | Test case preparation and Unit Testing | Release-2 |  | Not Started
12 | REQ12 | Prompt Questionnaries
|  |  | Get prompt questionnaries | Release-2 |  | Not Started
|  |  | UI functionality for Prompt Questinnaries | Release-2 |  | Not Started
|  |  | Test case preparation and Unit Testing | Release-2 |  | Not Started

## Burndown
Iteration | 0 | 2
Remaining | 59 | 0

## Release Phase
# | Release Phase/Milestone | Description
1 | Release-1 | Sprint-1 Release
2 | Release-2 | Sprint-2 Release