## Product Backlog
Final PoC Project | [6 empty] | Story point estimation
# | REQ ID | Features / Requirements - Level 1 | Features / Requirements - Level 2 | Release Phase/Milestone | Priority | Status | Initial Estimation | Sprint |  | Remarks
[7 empty] | 0 | 1 | 2
[7 empty] | 343 | 68 | 0
Application Management / Administration
1 | REQ1 | Registration and Login
|  |  | Registration for new user | Release-1 | P2 | Completed | 28 | 28
|  |  | Login page for registered user | Release-1 | P2 | Completed | 20 | 8
|  |  | Logout from application | Release-1 | P3 | Completed | 7 | 7
|  |  | UI functionality for profile | Release-1 | P3 | Completed | 25 | 25
|  |  | Test case preparation and Unit Testing | Release-1 |  | Not Started | 34
2 | REQ2 | Dashboard |  |  | P1
|  |  | Book Seat | Release-1 |  | In-Progress | 25
|  |  | View Pass | Release-1 |  | Not Started | 40
|  |  | View Booking | Release-1 |  | In-Progress | 15
|  |  | Modify Booking | Release-1 |  | In-Progress | 20
|  |  | Cancel Booking | Release-1 |  | In-Progress | 20
|  |  | UI functionality for dashboard | Release-1 |  | In-Progress | 44
|  |  | Test case preparation and Unit Testing | Release-1 |  | Not Started | 40
3 | REQ3 | Profile |  |  | P1
|  |  | View Profile | Release-1 |  | In-Progress | 25
|  |  | Modify Profile | Release-1 |  | In-Progress | 20
|  |  | UI functionality for Profile | Release-1 |  | Not Started | 22
|  |  | Test case preparation and Unit Testing | Release-1 |  | Not Started | 30
4 | REQ4 | Notification |  | Release-2
|  |  | Notification for Booked Seat | Release-2 |  | Not Started
|  |  | UI functionality for notification | Release-2 |  | Not Started
|  |  | Test case preparation and Unit Testing | Release-2 |  | Not Started
5 | REQ5 | Seat Booking and Tracking
|  |  | View Floor Map with availabel and booked seats | Release-2 |  | Not Started
|  |  | Select Floor and Book Seat | Release-2 |  | Not Started
|  |  | UI Functionality for seat booking and tracking | Release-2 |  | Not Started
|  |  | Test case preparation and Unit Testing | Release-2 |  | Not Started
6 | REQ6 | Admin functionalities
|  |  | Create booking | Release-2 |  | Not Started
|  |  | View and Record Booking Details | Release-2 |  | Not Started
|  |  | Approve and Reject Booking request | Release-2 |  | Not Started
|  |  | Scan QR and retrieve details | Release-2 |  | Not Started
|  |  | Add/Delete Seat | Release-2 |  | Not Started
|  |  | Add/Delete Room | Release-2 |  | Not Started
|  |  | Add/Delete Floor | Release-2 |  | Not Started
|  |  | UI Functionality for Admin functionalities | Release-2 |  | Not Started
|  |  | Test case preparation and Unit Testing | Release-2 |  | Not Started
7 | REQ7 | Prompt Questionnaries
|  |  | Get prompt questionnaries | Release-2 |  | Not Started
|  |  | UI functionality for Prompt Questinnaries | Release-2 |  | Not Started
|  |  | Test case preparation and Unit Testing | Release-2 |  | Not Started

## Burndown
Iteration | 0 | 2
Remaining | 343 | 0

## Release Phase
# | Release Phase/Milestone | Description
1 | Release-1 | Sprint-1 Release
2 | Release-2 | Sprint-2 Release