## Sprint-4.0 Retrospection
Project Name: TEAM 3 - DESKIFY
Sprint - 4.0 |  | Date: 07-Oct-2022
# | +ve | r | Action Item | Target Date | Responsible
1 | 98% of the planned tasks are completed in Sprint -1 |  |  | 07-APR-2022 (Sprint - 2) | Team
2 | Team co-ordination is excellent |  |  | 07-APR-2022 (Sprint - 2) | Team
2 | Unplanned tasks are completed |  |  | 07-APR-2022 (Sprint - 2) | Team
3 | Successful unit testing in every task |  |  | 07-APR-2022 (Sprint - 2) | Team
4 | Completion of task on time |  |  | 07-APR-2022 (Sprint - 2) | Team
5 |  | Initially, Poor planning and division of work | Over a time, an unanimous decision was taken on who is going to perfrom which task | 07-APR-2022 (Sprint - 2) | Team
6 |  | Iteration backlog is not updated before standup meeting | Team Members should update iteration backlog before standup meeting | 07-APR-2022 (Sprint - 2) | Team