## Sprint-1 Retrospection
Project Name: TEAM 3 - DESKIFY
Sprint - 1 |  | Date: 07-Oct-2022
# | +ve | r | Action Item | Target Date | Responsible
1 | 98% of the planned tasks are completed in Sprint -1 |  |  | 07-APR-2022 (Sprint - 2) | Team
2 | Team co-ordination is excellent |  |  | 07-APR-2022 (Sprint - 2) | Team
2 | Unplanned tasks are completed |  |  | 07-APR-2022 (Sprint - 2) | Team
3 | Successful unit testing in every task |  |  | 07-APR-2022 (Sprint - 2) | Team
4 | Completion of task on time |  |  | 07-APR-2022 (Sprint - 2) | Team
5 |  | Initially, Poor planning and division of work | Over a time, an unanimous decision was taken on who is going to perfrom which task | 07-APR-2022 (Sprint - 2) | Team
6 |  | Iteration backlog is not updated before standup meeting | Team Members should update iteration backlog before standup meeting | 07-APR-2022 (Sprint - 2) | Team

## Sprint-2 Retrospection
Project Name: TEAM 3 - DESKIFY
Sprint - 1 |  | Date: 07-Oct-2022
# | +ve | r | Action Item | Target Date | Responsible
1 | All the listed task in sprint 2 is completed |  |  |  | Team
2 | Team co-ordination is excellent |  |  |  | Team
3 | Division of work was better than previous sprint |  |  |  | Team
4 | Successful unit testing in every task |  |  |  | Team
5 | Team members worked even after shift time and during weekends. |  |  |  | Team
6 |  | Some task consumed extra time than estimated | Tried to be fast and reliable |  | Team
7 |  | Faced problems in Integrating backend with UI due to poor planning | Divided into multiple components and then integrated |  | Team